## Sheet1
WVAPA Chapter Strategic Plan - Implementation Schedule | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2024-01-01
Goal 1: Create a deep bench of well dispersed leadership
Strategy 1.1: Utilize a skills and interest survey to recruit leadership (Timeframe: 1-3 months)
1. Survey completed and info provided to executive leadership
2. Using survey results for future efforts - assign champions | bar: 2022-01-01 to 2022-02-01
Strategy 1.2: Identify key leadership needs of the organization such as Legislative Liaison and Professional Development Officer, Diversity, Equity and Inclusion or other (create job descriptions, how tasks break down, etc.) (Timeframe: 6-12 months)
1. Create job/task descriptions for each committee, review APA’s descriptions of committees | bar: 2022-01-01 to 2022-03-01
2. Create/recruit a membership committee. | bar: 2022-04-01 to 2022-06-01
3. Identify champion(s) for Legislative Committee. | bar: 2022-04-01 to 2022-06-01
4. Identify champion(s) for Professional Development committee (elective element). | bar: 2022-07-01 to 2022-12-01
Strategy 1.3: Create a succession plan for senior leadership to maintain organizational continuity (Timeframe: 6-12 months) | bar: 2023-01-01 to 2024-01-01
1. Create policy for executive leadership to determine leadership succession plan. | bar: 2022-07-01 to 2022-12-01
2. Create bite sized participation membership can take on to practice leadership roles. | bar: 2022-07-01 to 2022-12-01
Goal 2: Develop a budget and financial plan for the organization
Strategy 2.1: Establish a Finance Committee to support the Treasurer (Timeframe: 3-6 months)
1. Identify the role of the finance committee. | bar: 2022-01-01
2. Identify APA WV members interested in joining a finance committee through email request. | bar: 2022-01-01
3. Have the President (Jennie) appoint a minimum of three members to the committee. | bar: 2022-01-01
4. Convene the committee and begin to develop a fiscal 2022-2023 budget. | bar: 2022-02-01
5. Elect a finance chair | bar: 2022-02-01
Strategy 2.2: Develop a budget and a financial plan for the organization (Timeframe: 6-12 months)
1. Convene the committee and begin to develop a fiscal 2022-2023 budget. | bar: 2022-01-01
2. Draft final recommended budget by annual chapter meeting. | bar: 2022-05-01
3. Identify average annual revenue and expenditures. | bar: 2022-01-01
4. Finance committee will have to work with the other committees (to include executive committee) to identify programs, projects, training, and other work requiring funding support. | bar: 2022-04-01
5. Identify revenue needs and plan for new potential revenue sources. | bar: 2022-04-01
6. Implementing a reserve fund for unexpected expenditures or special projects. | bar: 2022-04-01
7. Forecast three to five years of budget. | bar: 2022-07-01
Goal 3: Broaden and diversify organization membership
Strategy 3.1: Revamp the WV APA website (in queue to get APA website) (Timeframe: 3-6 months)
1. Put Website on APA National Platform | bar: 2022-01-01 to 2022-03-01
2. Website Strategy for Content (Library / Q&A content / Site map / Who uploads?) (Create survey for members). | bar: 2022-01-01 to 2022-06-01
3. Create a Best Practices and Content Portal. | bar: 2022-01-01 to 2022-06-01
Strategy 3.2: Develop marketing materials that membership can share with potential partner organizations and professionals that shows the value and impact WVAPA offers and find ways for individual chapter members to promote the chapter through their day-to-day work (i.e., WV Chapter Logo on signature block) (Timeframe: 6-12 months).
1. Develop language/sound bite marketing packet about WVAPA chapter. | bar: 2022-01-01 to 2022-06-01
2. Developing marketing materials about WVAPA (pretty marketing materials). | bar: 2022-07-01 to 2022-12-01
3. Create video about chapter | bar: 2023-01-01 to 2024-01-01
Strategy 3.3: Identify individuals and groups for outreach and marketing membership opportunities (i.e., GIS mapping, WV Floodplain Association, transportation orgs, CDBG, other planning adjacent practitioners, private-sector planning professionals (Timeframe: 6-12 months).
1. Compiling master list of planning commissions. | bar: 2023-01-01 to 2024-01-01
2. Compiling master list Educational Institutions w/ Geography/Enviro Science/Engineering/Arch./Law/Poli Sci etc. | bar: 2023-01-01 to 2024-01-01
3. State Offices (DEP, DOT, DOE?, Econ dev) | bar: 2023-01-01 to 2024-01-01
4. Private Sector. | bar: 2023-01-01 to 2024-01-01
5. Schools (High School, Middle School, Elementary, etc.) – GIS tie in, 4-H, Comp Plans, DEI | bar: 2023-01-01 to 2024-01-01
6. Develop recruitment strategies for groups who have been traditionally underrepresented in the field Diversity, Equity, and Inclusion. | bar: 2023-01-01 to 2024-01-01
Goal 4: Provide continuing education and outreach for planning field in WV
Strategy 4.1: Create more professional credits and combined conference / education opportunities AICP (AIA, RSLA, CE, DOT, Annual Planning Conference, Brownfields Conference, Land Use Conference, public health officials) (Timeframe: 6-12 months)
1. Develop a calendar of events for state/regional conferences that may be of interest to members. | bar: 2022-01-01
2. Identify opportunities to collaborate on potential educational opportunities with neighboring chapters (that may or may not be unique to practitioners in Appalachia). | bar: 2022-01-01 to 2022-03-01
3. Connect with the APA’s Small Town and Rural Planning Division and other APA Chapters in Appalachia to determine if regional trainings, seminars or forums should/could be forged to support practitioners in more rural communities. | bar: 2022-01-01 to 2022-12-01
4. Continue to engage with the Mid-Atlantic Planning Collaborative (WV, MD, VA, DE and PA).
5. Engage Municipal League - Susan, Community Leadership Academy – Mike, County Commissioners Assoc. of WV, City Managers Association - Haws. | bar: 2022-01-01 to 2022-03-01
Strategy 4.2: Support/promote opportunities for AICP credits (Timeframe: 6-12 months)
1. Develop and send out survey to identify areas of interest for continual education credits for members. | bar: 2022-01-01 to 2022-03-01
2. Compile a list of state, regional and national organizations that offer continuing education credits approved by the APA that may be of interest to members (i.e., AIA, ASLA, IEDC, NDC, etc.). | bar: 2022-01-01 to 2022-06-01
3. Compile contact list of all citizen planners across the Mountain State (Planning Commissions and Board of Zoning Appeals) – work with Membership Committee. | bar: 2022-01-01 to 2022-07-01
4. Engage the Mid Atlantic Planning Collaborative to identify opportunities to host in-person conferences for training opportunities (every three or five years). | bar: 2022-01-01 to 2022-12-01
Goal 5: Develop legislative goals and strategy and engage constituents (socially and politically) at various levels, with planning
Strategy 5.1: Create legislative committee/liaison position and method for creating a legislative agenda (Timeframe: 0-12 months)
1. Identify the role of the legislative committee. | bar: 2022-01-01
2. Identify APA WV members interested in joining a legislative committee through email request. | bar: 2022-01-01
3. Have the President (Jennie) appoint a minimum of three members to the committee. | bar: 2022-01-01
4. Convene the committee. | bar: 2022-01-01
5. Elect a legislative committee chair. | bar: 2022-01-01
6. Committee determines how to select a legislative liaison or if this is a dual role for the chair. | bar: 2022-01-01 to 2022-02-01
7. Identify how to invite APA WV members to participate effectively with the legislative committee. | bar: 2022-01-01 to 2022-05-01
8. Committee to identify and track legislation of interest or concern to APA WV. | bar: 2022-01-01 to 2022-04-01
9. Create method for chapter wide input for legislative priorities. | bar: 2022-01-01 to 2022-07-01
10. Create plan to implement goal 5.3 (profile of people to advocate to, organizations, key figures, etc). | bar: 2022-01-01 to 2022-10-01
Strategy 5.2: Identify and engage individuals and groups to support legislative changes (such as the municipal league, association of counties, land use law clinic, council of Mayors, floodplain managers, etc.) (Timeframe: 6-12 months).
1. Create plan to implement goal 5.3; profile of people to advocate to, organizations, key figures, etc. | bar: 2022-01-01 to 2022-05-01
2. Identify from that list above of who are our top supporters who will help get our legislative goals accomplished. | bar: 2022-01-01 to 2022-10-01
3. Identify areas of policy agreement with these key supporters. | bar: 2022-01-01 to 2022-10-01
4. Begin to propose letters of support / concern with other organizations. | bar: 2022-01-01 to 2022-12-01
Goal 6: Implement programs, projects, and initiatives
Strategy 6.1: Create and distribute informational materials on planning education and planning issues to individuals and groups around the state (Timeframe: 6-12 months).
1. Compile contact list of state/regional organizations engaged in the planning profession (land use, transportation, economic, environment, etc.). | bar: 2022-01-01 to 2022-03-01
2. Identify and hire a consultant to development promotional materials for the organization (around the strategic plan and/or planning in WV more broadly – swag). Need to check with National. | bar: 2022-01-01 to 2022-06-01
3. Have promotional materials produced and ready for distribution. | bar: 2022-01-01 to 2022-09-01
4. Develop content and timeline to publish Public Service Announcements on a regular basis from the Chapter. | bar: 2022-01-01 to 2022-03-01
5. Establish social media platform and protocol for the Chapter (celebrate accomplishments, disseminate information). | bar: 2022-01-01 to 2022-09-01
6. Advocate for establishing a minor/major planning program in the State. | bar: 2023-01-01 to 2024-01-01
Strategy 6.2: Participate in National Community Planning Month (Timeframe: 6-12 months).
1. Research how APA Chapters engage citizen planners in the profession (from a program development and marketing perspective).
2. Develop a state-wide program/campaign to celebrate National Community Planning Month that focus on the Mountain State - Community engagement resources, Promotional resources (video), Financial resources and setup table at the Mountain Lair and other Universities around the State (recruitment effort). | bar: 2022-01-01 to 2022-08-01